## Slide 1: StratusLab Project Status
C. Loomis (CNRS/LAL)
PMB Meeting (Phone)
24 February 2011

## Slide 2: Current State of Project
Management/Dissemination
  No real management concerns, although Q4 will be hectic!
  StratusLab very visible in EU scientific community.
Development
  All major components in releases, exct. storage and service manager.
  Tools, support in place and working well (excepting Hudson hiccup).
Use of StratusLab
  Use and feedback from many communities; further push with v0.3.
  Interest from many sites for deploying cloud for their users.
Infrastructure
  Reference cloud running.
  Grid site running over StratusLab being certified.

## Slide 3: Deliverables/Milestones Approval
Approval of deliverable
  D5.2 (M6): Infrastructure Tool and Policy Specification
Approval of milestones
  MS2 (M4): Contact Procedures and Support Tools for Targeted Communities
  MS7 (M6) StratusLab Development, Certification and Release Procedures in Place

## Slide 4: Current Milestones
Milestones
  MS3 (M9): Creation of Virtual Appliances for Bioinformatics Community
  MS10 (M9): Initial virtual appliance repository
  MS14 (M9): Release of Cloud-like Management of Grid Services and Resources 1.0 Beta
Comments
  First two achieved; matter of creating milestone documents.
  Some integration of Claudia scheduled for Sprint 10; critical that some version (meeting minimal requirements) appear in the release.

## Slide 5: Upcoming Deliverables/Milestones
Deliverables
  MS8 (M10): Release of StratusLab 1.0 Beta
  MS11 (M10): Operation of Site Running StratusLab toolkit v1.0
  D6.2 (M11): Cloud-like Management of Grid Sites 1.0 Software
  D2.2 (M12): Report on Evaluation of StratusLab Products
  D3.2 (M12): Report on Dissemination, Collaboration and Standardization Activities
  D3.3 (M12): Exploitation and Sustainability First Plan
  D4.2 (M12): StratusLab Toolkit 1.0
  D4.3 (M12): First Year Software Integration Report
  D5.3 (M12): First Year Infrastructure Operations Report
  D6.3 (M12): First Year Cloud-like Management of Grid Sites Research Report
  D4.4 (M15): Reference Architecture for StratusLab Toolkit 2.0 (outline for EU review)
Comments
  Worry about making achieving D6.2—essentially full Claudia integration.
  Too many to handle in M12 also with QR4, PR1, and Forms C!
  Deadline for all Y1 reports will be 10 June 2011—earlier than usual.

## Slide 6: Removing Congestion…
Suggestion
  Require Tables of Contents in M10.
  Require draft content in M11.
Comment
  Achieving all deliverables on time will mean a concentration on these reports taking focus away from development of new features.

## Slide 7: Memoranda of Understanding
EGI
  Conduit to users and/or administrators?
  SLA for provision of software (with engagement for deployment)?
  Production of grid images by EGI?
  Responsibility for Marketplace after StratusLab?
EMI
  Currently use grid certificate software; formalize relationship?
  Need any changes to grid software?
  Outsource production of grid images to EMI?
ERINA+
  Rather one-sided MoU proposed.
  Would help us with impact and sustainability plans/deliverables.
  Would require significant effort on our part to provide information and participate.
EDGI
  Already collaborating at infrastructure/application level.
  Formalize this relationship?
Other Strategic Partners?

## Slide 8: Cloud Workshop
Steven has proposed a workshop on integration of cloud/virtualization technologies in the grid.
  My opinion is that this is a good idea.
  Time scale problematic—May—in parallel with numerous deliverables/milestones.
  Discussion…

## Slide 9: Partner Contrib. and Effort Levels
All partners are contributing significantly to project, but all are currently providing/using less effort than foreseen.
  There is no sense in spending less than the maximum amount defined by the EC.
  More effort planned by partners?
  Consider shifting of financing between partners?
  If reshuffling, this should be done ASAP to make effort effective.
Discussion…

## Slide 10: Review of Y1 Work Plan & Objectives
Change of large scale objectives:
  User visible cloud & cloud API moved from Y2 to Y1.
  Hybrid cloud investigations moved from Y1 to Y2.
  Appliance Repository  Marketplace and storage
Activity Objectives
  Generally all OK.
  Some concern for the integration/scope of WP6 software
Discussion…

## Slide 11: EU Review Planning
Dates
  Review tentatively scheduled for week of 4 July in Brussels.
  Must have all deliverables available by 10 June.
  Final Forms C (partner financial claims) must be available for review (possibly earlier).
Discussion…
  Feasibility of “dry run” for financial information.
  Advancing work on deliverables (already discussed).
  Scope/format for review. By WP? By partner? Demo?

## Slide 12: Post Project Follow-ons
General desire to continue the collaboration. How to achieve this (with funding!)?
Discussion…