## Slide 1: Etat d’avancement Lot Aimants
Projet Emblématique
Programme SESAME
With the support of
Cynthia VALLERAND
08/10/2018

## Slide 2: Context
  Nb of magnets and which ?
  6 Dipoles including 2 for the beam deviation (purple) and 4 for the energy selection of the beam (pink)
  9 Quadrupoles (red) for the beam focalisation
  6 Steerers for the beam trajectory correction

## Slide 3: Specifications
Field Homogeneity determines precision of beam energy.
DIPOLES |  |  | QUADRUPOLES | 
Bending angle (°) | 45 | 14 | Quantity | 12
Quantity | 4 (+2) | 2 | Gradient (T/m) | 28
Energy max. (MeV) | 150 |  | Iron length (m) | 0.2
Good field region (mm) | +/- 15 |  | Good field region (mm) | +/- 18
Gap (mm) | 40 |  | Energy max. (MeV) | 150
Iron length (m) | 1.2 | 0.2 |  | 

## Slide 4: Interactions
MAGNETS
Vacuum
Cooling
(air, water)
Beam Dynamics
Power supply
Management
Integration/gestion des interfaces
Alignment
Safety/Radioprotection
Logistique
Purchase/Contract

## Slide 5: Status : ECS DIPOLE
Initial parameters :
sx = 6.53mm => ±8sx = 105mm
sy = 1.43mm => ±10sy = 30mm
Deviation angle = 45°
E = 150MeV
GFR = ± 15mm
Gap = 40 mm
STATUS : Pre-design is finished

## Slide 6: Status : Quadrupoles
Recuperation of CTF3 quadrupoles (12) and steerers (6)
Power supplies ?

## Slide 7: Status : Quadrupoles
STATUS : Pre-design is finished
Initial parameters :
R = 20mm
k = 28m-2
E = 150 MeV
Integrated magnetic field B2 = -0.07063 T.m
Magnetic gradient G = -14.6059 T/m
Magnetic length = 366 mm

## Slide 8: What it remains to do
Design of 14° dipoles : March 2019
Finalisation of 45° ECS dipoles design : March 2019
Study of beam energy measurement dipoles with G. Quéméner : August 2019
Mechanical drawings of all dipoles for a tender call
    14° & 45° dipoles drawings : May 2019
Call for tender : July 2019 at the latest